## CASS Objectives Dashboard
CASS OVERVIEW AND QUARTERLY REPORT DASHBOARD TEMPLATE
Business Point of Contact: Wolfgang Zierer CASS Scientific Program Manager, University of Erlangen-Nuremberg, wolfgang.zierer@fau.de Date report submitted: October 25, 2024 Investment ID Start dates: May 1, 2024 End date: April 30, 2029
PC: Percent Complete: We look at the Key Result (metric) and estimate the percentage of work that has been completed by dividing the accomplished tasks by the total tasks assigned for that objective. This score can be low early in the project and even zero for a Team Objective that does not start until later in the programme. We are not expecting this score to necessarily show linear progress over the five years of the project.
PS: Progress Score: This is a score indicates, independently of the Percent Complete, if we are still on track to deliver the Key Results by the target date. We are expecting this to be green (0.7 - 0.9) for most objectives until significant risk to delivery by the target date is anticipated. A completed Key Result can be scored 1 and a dropped Key Result can be scored 0. To interpet the scores use the following guidelines: 0.9: Excellent progress with delivery assured by the target date. 0.7: On track and likely to deliver by the target date. 0.5: Lower than anticipated progress with some challenges or delays. 0.3: Low progress with significant challenges or delays. 0.1: Very low progress or no progress at all.
CASS Objectives and Key Results
Objective EM1: OPTIMIZING ASSIMILATE ALLOCATION TO STORAGE ROOTS
EM1.1_Manipulating shoot architecture (Uwe Sonnewald, FAU)
| PC | PS | TEAM OBJECTIVE | KEY RESULT (Metrics) | Assigned | Reporting Scientists | Start Date | Target Date | Dependencies (optional) | GoNoGo date | GoNoGo Metric
1.1.1 | 100% | 0.9 | EM1.1: Generate and validate constructs expressing GA2ox and DELLA. | Create 2 constructs for stem-specific reduction of GA-levels and 2 constructs for stem-specific expression of DELLA variants. | FAU | Uwe Sonnewald | Q2 2024 | Q3 2024
1.1.2 | 100% | 0.9 | EM1.1: Test transgenic cassava lines expressing GA2ox and DELLA under glasshouse conditions. | Isolation of the most promising lines from the up to 30 events provided from the transformation unit. Detailed greenhouse characterization for at least 3 independent lines, verfiying largely stem-specific transgene expression, reduction in plant axis height, reduction in bioactive GA content, gas exchange paramters, and greenhouse biomasses. | FAU | Uwe Sonnewald | Q2 2025 | Q4 2025 | Timely delivery of transgenic lines from TM2.1 | Q4 2025 | Go/No-go: Is the GA2ox and DELLA concept viable or are improvements possible? Key parameters for GA2ox/DELLA constructs in the greenhouse: - Largely stem-specific transgene expression - Significant reduction in bioactive GA content compared to VC (only GA2ox) - Significant reduction in plant axis height compared to VC - Photosynthetic parameters are no less than 10% worse compared to VC - Greenhouse storage root formation after 3-month is not significantly worse compared to VC
1.1.3 | 0% | 0.7 | EM1.1: Analysis of agronomic parameters and sample analysis for CFT 2026 Taichung of GA2ox and DELLA field sample material including transgene expression and GA content and carbohydrate analysis | Significant improvements in harvest index and strorage root yield can be observed against VC. Leaf-, stem-, and storage root material collected from the field was analyzed. Largely stem-specific transgene expression and reduction in bioactive GA content is verified in the field sample material. Storage root starch concentration is not decreased. | FAU | Uwe Sonnewald | Q2 2026 | Q2 2027 | Sample delivery by TM4.1 | Q2 2027 | Go/No-go: Is there value in another round of CFTs or redesigning GA2ox and DELLA constructs? Key parameters for the GA2ox/DELLA constructs in field trial 1: - Largely stem-specific transgene expression - Significant reduction in bioactive GA content compared to VC (only GA2ox) - Significant reduction in plant axis height compared to VC - Significant increase in harvest index compared to VC - Significant improvement in storage root yield compared to VC
1.1.4 | 0% | 0.7 | EM1.1: Analysis of agronomic parameters and sample analysis for CFT 2027 Taichung of GA2ox and DELLA field sample material including transgene expression, GA content and carbohydrate analysis | Significant improvements in harvest index and strorage root yield can be observed against VC. Leaf-, stem-, and storage root material collected from the field was analyzed. Largely stem-specific transgene expression and reduction in bioactive GA content is verified in the field sample material. Storage root starch concentration is not decreased. | FAU | Uwe Sonnewald | Q2 2027 | Q2 2028 | Sample delivery by TM4.1 | Q2 2028 | Go/No-go: Is there value in another round of CFTs or redesigning GA2ox and DELLA constructs? Key parameters for the GA2ox/DELLA constructs in field trial 2: - Largely stem-specific transgene expression - Significant reduction in bioactive GA content compared to VC (only GA2ox) - Significant reduction in plant axis height compared to VC - Significant increase in harvest index compared to VC - Significant improvement in storage root yield compared to VC
EM1.2_Limiting lateral transport losses through active phloem (re-)loading (Ekhardt Neuhaus, RPTU)
| PC | PS | TEAM OBJECTIVE | KEY RESULT (Metrics) | Assigned | Reporting Scientists | Start Date | Target Date | Dependencies (optional) | GoNoGo date | GoNoGo Metric
1.2.1 | 100% | 0.7 | Test transgenic cassava lines expressing AKT2/AAP1/SUC2 under glasshouse conditions. | Detailed greenhouse characterization for at least 3 events verfiying transgene expression in transport tissues, analyzed construct-specific changes in metabolite distribution including amino acids (AAP1), potassium (AKT2), sucrose (SUC2). Determined changes in carbon allocation through 11C-PET scanning where appropriate. | RPTU/MPI-MPP | Ekkehard Neuhaus | Prior | Q4 2024
1.2.2 | 100% | 0.7 | Analysis of agronomic parameters and sample analysis for CFT 2024 relevant field sample material including transgene expression and metabolite analysis. | Transgene expression in transport tissues verified. Changes in amino acid (AAP1), ion (AKT2), and carbohydrate (SUC2, all) content verified. | RPTU/MPI-MPP | Ekkehard Neuhaus | Prior | Q2 2025 |  | Q2 2025 | Go/No-go: Is the AKT2/AAP1/SUC2 concept viable or are improvements possible? Key parameters for AKT2/AAP1/SUC2 constructs in field trial 1: - Transgene expression in phloem tissues confirmed - Significant changes in the content or distribution of amino acids (AAP1), potassium (AKT2), and carbohydrates (AAP1/AKT2/SUC2) - Storage root starch concentration is not significantly reduced compared to VC - Storage root yield is significantly increased compared to VC
1.2.3 | 100% | 0.7 | Analysis of agronomic parameters and sample analysis for CFT 2025 of relevant field sample material including transgene expression and metabolite analysis. | Transgene expression in transport tissues verified. Changes in amino acid (AAP1), ion (AKT2), and carbohydrate (SUC2, all) content verified. | RPTU/MPI-MPP | Ekkehard Neuhaus | Q2 2025 | Q2 2026
1.2.4 | 85% | 0.7 | Continued analysis of existing AKT2 cassava lines | Analyze existing AKT2 cassava lines (TMS60444 and other genomic backgrounds that are being created) under control and different abiotic stress conditions (e.g. water loging, drought stress) and try to elucidate the mode of action | FAU/RPTU/ETH | Ekkehard Neuhaus | Q1 2025 | Q1 2026
1.2.5 | 100% | 0.7 | Generate additional constructs centered on potassium transport | Generate new constructs centered on potassium transport: - New AKT2 promoter-gene combinations - Combination of AKT2 and GPT, NTT - New OsHAK18 target gene | FAU/RPTU/ETH | Ekkehard Neuhaus | Q2 2025 | Q2 2026
1.2.6 | 0% | 0.7 | Test transgenic cassava lines created in 1.2.5 under glasshouse conditions | Isolation of the most promising lines from the up to 30 events provided from the transformation unit. Detailed greenhouse characterization of at least 3 independent lines characterised for transgene expression and analyzed for changes in metablolite distribution and content. | RPTU/FAU/ETH | Ekkehard Neuhaus | Q2 2026 | Q2 2027 | Successful transformation in TM2.1 | Q2 2027 | Go/No-go: Are these new constructs viable or are improvements possible? Key parameters for these new constructs in the greenhouse: - Tissue-specific transgene expression verified - Favorable changes in source-sink allocation confirmed
1.2.7 | 0% | 0.7 | Analysis of agronomic parameters and sample analysis for CFT2027 of relevant field sample material from different potassium transport lines | Transgene expression analyzed in different tissues with specific expression in target tissues. Improved source-sink allocation verified. | RPTU | Ekkehard Neuhaus | Q2 2027 | Q2 2028 | Successful sample delivery (1.2.7) | Q2 2028 | Go/No-go: Are these new constructs viable or are improvements possible? Key parameters for these new constructs in field trial 1: - Tissue-specific transgene expression verified - Significant storage root yield increase compared to VC - Other parameters TBD (dependent on the particular constructs created)
1.2.8 | 0% | 0.7 | Analysis of agronomic parameters and sample analysis for CFT 2028 of relevant field sample material from different potassium transport lines | Transgene expression analyzed in different tissues with specific expression in target tissues. Improved source-sink allocation verified. | RPTU | Ekkehard Neuhaus | Q2 2028 | Q2 2029 | Successful sample delivery by TM4.1 | Q2 2029 | Go/No-go: Are these new constructs viable or are improvements possible? Key parameters for these new constructs in field trial 2: - Tissue-specific transgene expression verified - Significant storage root yield increase compared to VC - Other parameters TBD (dependent on the particular constructs created)
EM1.3_Transport and allocation modelling
| PC | PS | TEAM OBJECTIVE | KEY RESULT (Metrics) | Assigned | Reporting Scientists | Start Date | Target Date | Dependencies (optional) | GoNoGo date | GoNoGo Metric
1.3.1 | 100% | 0.5 | EM1.3: Data collection: Non-aqueous fractionation of cassava leaves and determination of phloem sap composition and concentration. | Proper subcellular separation is validated by marker enzyme activity and proper phloem sap isolation is validated through metabolite measurements | RPTU | Lee Sweetlove | Q2 2024 | Q2 2025 | Experimental support through group Neuhaus | Q2 2025 | Go/no-go: Can the necessary experimental data be created or a possible replacement identified?
1.3.2 | 95% | 0.5 | EM1.3: Data collection: 13CO2 feeding experiment and analysis of label redistribution in stems. | Tissue-specific 13CO2 label distribution can be determined by mass spectrometry. | MPI-MPP | Lee Sweetlove | Q2 2024 | Q2 2025 | Experimental support through group Fernie | Q2 2025 | Go/no-go: Can the necessary experimental data be created or a possible replacement identified?
1.3.3 | 95% | 0.5 | EM1.3: Data collection: Microscopy analysis of source leaf and stem cellular anatomy. | EM pictures and data evaluation reveals cellular and sub-cellular dimensions. | ETH | Lee Sweetlove | Q2 2024 | Q2 2025 | Experimental support through group Zeeman | Q2 2025 | Go/no-go: Can the necessary experimental data be created or a possible replacement identified?
1.3.4 | 0% | 0.7 | EM1.3: A stem anatomy model to identify the optimal balance between stem and sucrose leak/reloading rates | Model constains sufficient cell types/compartments to describe the routes of sucrose leak and reloading. Model is atom and charged balanced. Model can simulate metabolic demands of stem growth, starch sotrage and maintenance. Model can simulate the metabolic cost of phloem reloading. Model can incorporate 11C velocity and leak/reloading data. Model can incorporate 13C whole plant carbon distribution data. | Oxford | Lee Sweetlove | Q3 2026 | Q2 2027 |  | Q2 2027 | Go/no-go: Can the model predict the biochemical phenotype of WT and/or trangenic plants?
1.3.5 | 0% | 0.7 | EM1.3: A data-driven mechanistic model of phloem and xylem transport between source and sink, which includes K+ distribution and AKT2 to explain why overxpression of AKT2var leads to increased phloem transport | Model can simulate kinetics of sucrose leak and reloading in the phloem and the effect of AKT2 and AKT2var on this. Model can simulate phloem flow velocity and couple this to concentrations predicted by sucrose leak/reloading model. | Oxford | Lee Sweetlove | Q3 2026 | Q2 2027 |  | Q2 2027 | Go/no-go: Can the model predict/explain the biochemical phenotpye of AKT2var transgenic plants?
1.3.6 | 0% | 0.7 | EM1.3: A ranked list of engineering target combinations for improved phloem transport for prioritisation of gene stacking experiments | A ranked list of engineering target combinations for improved phloem transport for prioritisation of gene stacking experiments | Oxford | Lee Sweetlove | Q2 2027 | Q2 2028 | 1.3.4 and/or 1.3.5 model are constricted and validated. | Q2 2028 | Go/no-go: Can the models generate a ranked list of targets or a ranked list of target combinations?
Objective EM2: Increasing sink strength by optimizing xylem parenchyma cell formation in storage roots
EM2.1_Manipulation of OVAC and cytokinin metabolism or signaling
| PC | PS | TEAM OBJECTIVE | KEY RESULT (Metrics) | Assigned | Reporting Scientists | Start Date | Target Date | Dependencies (optional) | GoNoGo date | GoNoGo Metric
2.1.1 | 100% | 0.9 | EM2.1: Generate constructs with alterations in OVAC and storage root-specific cytokinin overexpression. | Create at least 3 constructs altering OVAC and storage root-specific cytokinin overexpression. | HU/FAU/ETH | Yka Helariutta | Q2 2024 | Q3 2024
2.1.2 | 85% | 0.5 | EM2.1: Test transgenic cassava lines with alterations in OVAC and storage root-specific cytokinin overexpression under glasshouse conditions. | Isolation of the most promising lines from the up to 30 events provided from the transformation unit. Detailed greenhouse characterization for at least 3 independent transgenic lines per construct. Constructs characterised for tissue-specific transgene expression, storage root radial growth, hormone content, and effect of wildtype grafting where appropriate. | HU/FAU | Yka Helariutta | Q2 2025 | Q4 2025 | Timely delivery of transgenic lines from TM2.1 | Q4 2025 | Go/No-go: Are these new constructs viable or are improvements possible? Key parameters for OVAC and CK constructs in the greenhouse: - Tissue-specific transgene expression verified - Alterations in hormone contents analysed - Grafting of ovac shoot and WT rootstock significantly increases secondary growth - Significant increase in storage root radial growth
2.1.3 | 25% | 0.7 | EM2.1: Analysis of agronomic parameters and sample analysis for CFT 2026 of OVAC and cytokinine field sample material including transgene expression, cytokinine and carbohydrate measurements | Tissue specific transgene expression validated and storage root cytokinine and carbohydrate levels analyzed. | HU/FAU | Yka Helariutta | Q2 2026 | Q2 2027 | Sample delivery by TM4.1 | Q2 2027 | Go/No-go: Is there value in another round of CFTs or redesigning the OVAC/CK constructs? Key parameters for OVAC and CK constructs in field trial 1: - Tissue-specific transgene expression verified - Alterations in hormone contents analysed - Grafting of ovac shoot and WT rootstock significantly increases secondary growth - Significant increase in storage root radial growth
2.1.4 | 0% | 0.7 | EM2.1: Analysis of agronomic parameters and sample analysis for CFT 2027 of OVAC and cytokinine field sample material including transgene expression, cytokinine and carbohydrate measurements | Tissue specific transgene expression validated and storage root cytokinine and carbohydrate levels analyzed. | HU/FAU | Yka Helariutta | Q2 2027 | Q2 2028 | Sample delivery by TM4.1 | Q2 2028 | Go/No-go: Is there value in another round of CFTs or redesigning the OVAC/CK constructs? Key parameters for OVAC and CK constructs in field trial 2: - Tissue-specific transgene expression verified - Alterations in hormone contents analysed - Grafting of ovac shoot and WT rootstock significantly increases secondary growth - Significant increase in storage root radial growth
EM2.2_Manipulation of downstream factors involved in xylem parenchyma cell formation
| PC | PS | TEAM OBJECTIVE | KEY RESULT (Metrics) | Assigned | Reporting Scientists | Start Date | Target Date | Dependencies (optional) | GoNoGo date | GoNoGo Metric
2.2.1 | 100% | 0.7 | EM2.2: Generate constructs with storage root-specific overexpression of transcription factors involved in xylem parenchyma cell formation under glasshouse conditions. | Create at least 2 constructs for storage root-specific overexpression of downstream factors involved in the control of secondary growth | HU/FAU | Ari-Pekka Mähönen | Q2 2024 | Q3 2024
2.2.2 | 65% | 0.5 | EM2.2: Test transgenic cassava lines expressing storage root-specific overexpression of transcription factors involved in xylem parenchyma cell formation under glasshouse conditions. | Isolation of the most promising lines from the up to 30 events provided from the transformation unit. Detailed greenhouse characterization for at least 3 independent lines. Lines characterised for transgene expression, storage root radial growth, transcriptional changes, and cellular anatomy. | HU/FAU | Ari-Pekka Mähönen | Q2 2025 | Q4 2025 | Successful transformation in TM2.1 | Q4 2025 | Go/No-go: Are these new LBD constructs viable or are improvements possible? Key parameters for transcription factor constructs in the greenhouse: - Tissue-specific transgene expression verified - Changes in transcriptome profile verified - Significant increase in storage root radial growth
2.2.3 | 0% | 0.5 | EM2.2: Analysis of agronomic parameters and sample analysis for CFT 2026 of field sample material from transcription factor overexpression lines including transgene expression and carbohydrate content | Tissue specific transgene expression validated and carbohydrate levels analyzed. | HU/FAU | Ari-Pekka Mähönen | Q2 2026 | Q2 2027 | Sample delivery by TM4.1 | Q2 2027 | Go/No-go: Is there value in another round of CFTs or redesigning LBD constructs? Key parameters for LBD constructs in field trial 1: - Tissue-specific transgene expression verified - Significant increases in storage root radial growth or storage root yield
2.2.4 | 0% | 0.7 | EM2.2: Analysis of agronomic parameters and sample analysis for CFT 2027 of field sample material from transcription factor overexpression lines including transgene expression and carbohydrate content | Tissue specific transgene expression validated and carbohydrate levels analyzed. | HU/FAU | Ari-Pekka Mähönen | Q2 2027 | Q2 2028 | Sample delivery by TM4.1 | Q2 2028 | Go/No-go: Is there value in another round of CFTs or redesigning LBD constructs? Key parameters for LBD constructs in field trial 2: - Tissue-specific transgene expression verified - Significant increases in storage root radial growth or storage root yield
2.2.5 | 0% | 0.7 | EM2.2: Generate constructs with single-cell RNA-Seq-derived candidates for 5 promoter-reporter constructs and 5 storage (xylem) parenchyma formation gene candidates. | Create at least 3 constructs for storage root-specific overexpression of target transcription factors. | HU/FAU | Ari-Pekka Mähönen | Q2 2026 | Q3 2026 | Successful single cell RNA sequencing in TM3.2.
2.2.6 | 0% | 0.7 | EM2.2: Create and test transgenic cassava lines for single-cell RNA-Seq-derived candidates for five promoter-reporter constructs and 5 storage (xylem) parenchyma formation gene candidates under glasshouse conditions. | Isolation of the most promising lines from the up to 30 events provided from the transformation unit. Detailed greenhouse characterization for at least 3 independent lines. Characterization includes transgene validation, transcriptional profiling, storage root radial growth determination, and cellular anatomy analysis. | HU/FAU/ETH | Ari-Pekka Mähönen | Q2 2027 | Q3 2027 | Successful transformation in TM2.1 | Q4 2027 | Go/No-go: Are these new single cell RNA-Seq-derived constructs viable or are improvements possible? Key parameters for transcription factor constructs in the greenhouse: - Tissue-specific transgene expression verified - Changes in transcriptome profile verified - Significant increase in storage root radial growth
2.2.7 | 0% | 0.7 | EM2.2: Sample analysis for CFT 2028 of field sample material from transcription factor overexpression lines including transgene expression, sugar and starch content. | Tissue specific transgene expression validated and carbohydrate levels analyzed. | HU/FAU | Ari-Pekka Mähönen | Q2 2028 | Q2 2029 | Sample delivery by TM4.1 | Q2 2029 | Go/No-go: Is there value in another round of single cell RNA-Seq-derived constructs or are improvements possible? Key parameters for transcription factor constructs in field trial 1: - Tissue-specific transgene expression verified - Changes in transcriptome profile verified - Significant increase in storage root radial growth
EM3_Increasing sink strength by optimizing metabolic flux in storage roots
EM3.1_Optimization of sucrolytic cleavage and glycolosis
| PC | PS | TEAM OBJECTIVE | KEY RESULT (Metrics) | Assigned | Reporting Scientists | Start Date | Target Date | Dependencies (optional) | GoNoGo date | GoNoGo Metric
3.1.1 | 100% | 0.9 | EM3.1: Generate new constructs aimed at improved sucrose cleavage/glycolysis. | Create at least 3 constructs for new designs aimed at improved sucrose cleavage and/or glycolysis. | MPI-MPP/FAU/ETH | Alisdair Fernie | Q2 2024 | Q3 2024
3.1.2 | 75% | 0.7 | EM3.1: Test transgenic cassava lines with new contructs aimed at improved sucrose cleavage/glycolysis under glasshouse conditions. | Isolation of the most promising lines from the up to 30 events provided from the transformation unit. Detailed greenhouse characterization for at least 3 independent lines with new contructs aimed at improved sucrose cleavage/glycolysis. Lines are characterised for transgene expression, enzyme activity, metabolite profile, and storage root yield. | MPI-MPP | Alisdair Fernie | Q3 2025 | Q3 2026 | Successful transformation in TM2.1 | Q3 2026 | Go/No-go: Are these new constructs targeting sucrose cleavage or glycolysis viable or are improvements possible? Key parameters for sucrose cleavage/glycolysis constructs in the greenhouse: - Tissue-specific transgene expression verified - Changes in enzyme activity verified (e.g. SUS) - Changes in metabolite profile verified - Starch concentration is not significantly reduced - Greenhouse storage root yield is at least on the level of the VC
3.1.3 | 25% | 0.7 | EM3.1: Analysis of agronomic parameters and sample analysis for CFT 2026 material from sucrose cleavage/glycolysis lines including transgene expression, enzyme activity, and metabolite content. | Transgene expression analyzed in different tissues with specific expression in storage roots. Changes in enzyme activity and metabolite profiles verified. | MPI-MPP | Alisdair Fernie | Q2 2026 | Q2 2027 | Sample delivery by TM4.1 | Q2 2027 | Go/No-go: Is there value in another round of CFTs or redesigning sucrose cleavage/glycolysis constructs? Key parameters for sucrose cleavage/glycolysis constructs in field trial 1: - Tissue-specific transgene expression verified - Changes in enzyme activity verified (e.g. SUS) - Changes in metabolite profile verified - Starch concentration is not significantly reduced - Significant increase in storage root yield
3.1.4 | 0% | 0.7 | EM3.1: Analysis of agronomic parameters and sample analysis for CFT 2027 material from sucrose cleavage/glycolysis lines including transgene expression, enzyme activity, and metabolite content. | Transgene expression analyzed in different tissues with specific expression in storage roots. Changes in enzyme activity and metabolite profiles verified. | MPI-MPP | Alisdair Fernie | Q2 2027 | Q2 2028 | Sample delivery by TM4.1 | Q2 2028 | Go/No-go: Is there value in another round of CFTs or redesigning sucrose cleavage/glycolysis constructs? Key parameters for sucrose cleavage/glycolysis constructs in field trial 2: - Tissue-specific transgene expression verified - Changes in enzyme activity verified (e.g. SUS) - Changes in metabolite profile verified - Starch concentration is not significantly reduced - Significant increase in storage root yield
3.1.5 | 0% | 0.5 | EM3.1: Generate constructs expressing model-prediction genetic elements (to be nominated later). | Create at least 3 constructs for new contructs with candidates element predicited from metabolic modeling. | MPI-MPP/Oxford/FAU | Lee Sweetlove | Q2 2025 | Q3 2025 | Model candidates nominated from EM3.4.
3.1.6 | 0% | 0.7 | EM3.1: Create and test transgenic cassava lines expressing model-prediction genetic elements under glasshouse conditions. | Isolation of the most promising lines from the up to 30 events provided from the transformation unit. Detailed greenhouse characterization concluded for at least 3 independent lines per new contructs predicited from metabolic modeling. Lines are characterised for transgene expression, metabolic profile, and storage root yield. | MPI-MPP | Alisdair Fernie | Q2 2026 | Q3 2027 |  | Q3 2027 | Go/No-go: Are these new model-derived constructs viable or are improvements possible? Key parameters for model-derived constructs in the greenhouse: - Transgene expression verified - Other parameters TBD (dependent on the target gene)
3.1.7 | 0% | 0.7 | EM3.1: Analysis of agronomic parameters and sample analysis for CFT 2028 of field sample material. | Transgene expression analyzed in different tissues with specific expression in storage roots. Changes in enzyme activity and/or metabolite profiles verified. | MPI-MPP | Alisdair Fernie | Q2 2028 | Q2 2029 |  | Q2 2029 | Go/No-go: Is there value in another round of CFTs or redesigning model-derived constructs? Key parameters for model-derived constructs in the greenhouse: - Transgene expression verified - Other parameters TBD (dependent on the target gene)
EM3.2_Optimization of starch-precursor delivery to amyloplasts
| PC | PS | TEAM OBJECTIVE | KEY RESULT (Metrics) | Assigned | Reporting Scientists | Start Date | Target Date | Dependencies (optional) | GoNoGo date | GoNoGo Metric
3.2.1 | 100% | 0.9 | EM3.2: Generate constructs with PPase/GPT/NTT/PGM/glgC constructs and combinations. | Create at least 5 constructs expressing PPase/GPT/NTT/PGM/glgC constructs. | FAU | Wolfgang Zierer | Q2 2024 | Q3 2024
3.2.2 | 90% | 0.5 | EM3.2: Create and test transgenic cassava lines expressing PPase/GPT/NTT/PGM/glgC constructs under glasshouse conditions. | Isolation of the most promising lines from the up to 30 events provided from the transformation unit. Detailed greenhouse characterization concluded for at least 3 independent transgenic lines expressing PPase/GPT/NTT/PGM/glgC constructs. Lines are characterised for transgene expression, enzyme activity, carbohydrate content, and storage root yield | FAU/ETH | Wolfgang Zierer | Q2 2025 | Q3 2025 | Successful transformation in TM2.1 | Q3 2025 | Go/No-go: Are these new constructs targeting PPase/GPT/NTT/PGMp/glgC viable or are improvements possible? Key parameters for PPase/GPT/NTT/PGM cop/glgC constructs in the greenhouse: - Tissue-specific transgene expression verified - Changes in enzyme activity verified (e.g. PGMp, glgC) - Changes in carbohydrate metabolism verified - Starch concentration is not significantly reduced - Greenhouse storage root yield is at least on the level of the VC
3.2.3 | 0% | 0.7 | EM3.2: Analysis of agronomic parameters and sample analysis for CFT 2026 of field sample material from PPase/GPT/NTT/PGM/glgC lines including transgene expression, enzyme activity, and carbohydrate content | Verified tissue-specific transgene expression, enzyme activity, and carbohydrate content | FAU | Wolfgang Zierer | Q2 2026 | Q2 2027 | Sample delivery by TM4.1 | Q2 2027 | Go/No-go: Are these new constructs targeting PPase/GPT/NTT/PGMp/glgC viable or are improvements possible? Key parameters for PPase/GPT/NTT/PGM cop/glgC constructs in field trial 1: - Tissue-specific transgene expression verified - Changes in enzyme activity verified (e.g. PGMp, glgC) - Changes in carbohydrate metabolism verified - Starch concentration is not significantly reduced - Significant increase in storage root yield
3.2.4 | 0% | 0.7 | EM3.2: Analysis of agronimic paramters and sample analysis for CFT 2028 of field sample material from PPase/GPT/NTT/PGM/glgC lines including transgene expression, enzyme activity, and carbohydrate content | Verified tissue-specific transgene expression, enzyme activity, and carbohydrate content | FAU | Wolfgang Zierer | Q2 2027 | Q2 2028 | Sample delivery by TM4.1 | Q2 2028 | Go/No-go: Are these new constructs targeting PPase/GPT/NTT/PGMp/glgC viable or are improvements possible? Key parameters for PPase/GPT/NTT/PGM cop/glgC constructs in field trial 2: - Tissue-specific transgene expression verified - Changes in enzyme activity verified (e.g. PGMp, glgC) - Changes in carbohydrate metabolism verified - Starch concentration is not significantly reduced - Significant increase in storage root yield
EM3.3_Starch granule initiation and growth
| PC | PS | TEAM OBJECTIVE | KEY RESULT (Metrics) | Assigned | Reporting Scientists | Start Date | Target Date | Dependencies (optional) | GoNoGo date | GoNoGo Metric
3.3.1 | 100% | 0.9 | EM3.3: Generate first generation constructs with single and multigene constructs (PTST2, MFP1, MRC, SS4, ESV1, LESV1). | Create constructs expressing single and multi-gene combinations of the 4 target genes PTST2, MFP1, MRC, SS4 plus knockouts in ESV1 and LESV1. | ETH | Sam Zeeman | Prioir | Q2 2024
3.3.2 | 75% | 0.7 | EM3.3: Test transgenic cassava lines expressing single and multigene constructs with PTST2, MFP1, MRC, SS4, ESV1, LESV1 under glasshouse conditions. | Detailed greenhouse characterization of at least 3 independent trangenic lines expressing single and multi-gene combinations of 4 genes plus knockouts in ESV1 and LESV1. Lines are characterized for amylose content, amylopectin structure, starch concentration, granule size, granule morphology, and above and below-ground parameters. | ETH | Sam Zeeman | Q2 2024 | Q4 2025 | Successful transformation in TM2.1 | Q4 2025 | Go/No-go: Is there value in entering these new lines, PTST2, MFP1, MRC, SS4 plus knockouts in ESV1 and LESV1 into CFTs? Key parameters for PTST2, MFP1, MRC, SS4, ESV1, LSV1 constructs in greenhouse: - Verified transgene expression in storage roots - Determination of amylose content and amylopectin structure - Determination of starch concentration, granule size and morphology - No significant reduction of storage root yield in the greenhouse
3.3.3 | 50% | 0.7 | EM3.3: Analysis of agronomic parameters and sample analysis for CFT 2024/2025 of field sample material from PTST2, MFP1, MRC, SS4, ESV1, LESV overexpression/KO lines lines including transgene expression, enzyme activity, and carbohydrate content | Verified tissue-specific transgene expression, amylose content, amylopectin structure, starch granule size and morphology, and starch content | ETH | Sam Zeeman | Q2 2026 | Q2 2027 | Sample delivery by TM4.1 | Q2 2027 | Go/No-go: Is there value in another round of CFTs or redesigning PTST2, MFP1, MRC, SS4, ESV1, LESV1 constructs? Key parameters for PTST2, MFP1, MRC, SS4, ESV1, LSV1 constructs in field trial 1: - Verified transgene expression in storage roots - Determination of amylose content and amylopectin structure - Determination of starch concentration, granule size and morphology - Significant increase in storage root yield compared to VC and/or significant improvement in starch quality parameters
3.3.4 | 0% | 0.7 | EM3.3: Analysis of agronomic parameters and sample analysis for CFT 2026 of field sample material from PTST2, MFP1, MRC, SS4, ESV1, LESV lines including transgene expression, starch quantity and quality parameters | Verified tissue-specific transgene expression, amylose content, amylopectin structure, starch granule size and morphology, and starch content | ETH | Sam Zeeman | Q2 2027 | Q2 2028 | Sample delivery by TM4.1 | Q2 2028 | Go/No-go: Is there value in another round of CFTs or redesigning PTST2, MFP1, MRC, SS4, ESV1, LESV1 constructs? Key parameters for PTST2, MFP1, MRC, SS4, ESV1, LSV1 constructs in field trial 2: - Verified transgene expression in storage roots - Determination of amylose content and amylopectin structure - Determination of starch concentration, granule size and morphology - Significant increase in storage root yield compared to VC and/or significant improvement in starch quality parameters
3.3.5 | 0% | 0.7 | EM3.3: Generate second generation constructs based on the best performing constructs from EM3.2 (Starch-precursory delivery) and EM3.3 (Starch granule initiation and growth) combined. | Create at least 2 constructs based on the best performing constructs from EM3.2 (Starch-precursory delivery) and EM3.3 (Starch granule initiation and growth) combined. | ETH/FAU | Sam Zeeman | Q1 2026 | Q2 2026
3.3.6 | 0% | 0.7 | EM3.3: Glasshouse testing of second generation construct cassava lines based on the best performing constructs from EM3.2 (Starch-precursory delivery) and EM3.3 (Starch granule initiation and growth) combined. Transformation of farmer-preferred cultivar(s) and/or TMS60444. Line selection and greenhouse analysis. Plantlet multiplication of selected lines and greenhouse cultivation. Starch characterisation from storage roots of greenhouse cultivated plants. | Testing of a selection of ≥10 independent single insertion lines via ddPCR with confirmation of all transgenes via agarose gel electrophoresis or microfluidics, determination of amylose content, amylopectin structure, starch concentration starch granule size, Starch granule morphology and above- and belowground parameters. | ETH/FAU | Sam Zeeman | Q2 2027 | Q2 2028 | Successful transformation in TM2.1 | Q3 2028 | Go/No-go: Is there value in entering these combined lines (EM3.2 & EM3.3) into CFTs? Key parameters for combined constructs in greenhouse: - Verified transgene expression in storage roots - Determination of amylose content and amylopectin structure - Determination of starch concentration, granule size and morphology - No significant reduction of storage root yield in the greenhouse
3.3.7 | 0% | 0.7 | EM3.3: Transformation of best performing constructs into additional cassava genotypes. | Isolation of at least 30 plant lines with PCR valdiated T-DNA insertions. | ETH/FAU/NRCRI | Sam Zeeman | Prior | Q3 2027
EM3.4_Model-based predictions
| PC | PS | TEAM OBJECTIVE | KEY RESULT (Metrics) | Assigned | Reporting Scientists | Start Date | Target Date | Dependencies (optional) | GoNoGo date | GoNoGo Metric
3.4.1 | 100% | 0.5 | EM3.4: Experimental data for model collected. Non-aqueous fractionation of cassava roots. 13CO2 feeding experiments and 11CO2-PET analysis of label redistribution in cassava. Microscopy analysis of root parenchyma cell anatomy. | Proper subcellular separation is validated by marker enzyme activity. Tissue-specific 13C-label distribution and 11C-label distribution can be determined by mass spectrometry and PET. EM pictures and data evaluation reveals cellular and sub-cellular dimensions. Experimental data is made available in database. | RPTU/MPI-MPP/ETH | Lee Sweetlove | Q2 2024 | Q4 2024 |  | Q4 2024 | Go/no-go: Can the necessary experimental data be created or a possible replacement identified?
3.4.2 | 100% | 0.5 | EM3.4: Build and analyse storage root parenchyma metabolic model. Assemble stoichiometric matrix of root parenchyma primary metabolism guided by transcriptome data. | Model can catabolize incoming sugars and convert to starch and other biomass components. Model is atom and charged balanced. Model predicts sucrose catabolism by SUS, starch synthesis via AGPase, glycolysis and oxidative pentose phosphate pathway flux. Adding Kcat constraints alters baseline flux solution and predicts optimal investment in enzyme resources. 11C/13C and metabolite data alters predicted fluxes in the model. Model can predict starch flux phenotype of select transgenic lines (e.g. SUS/GPT/NTT/AGPase). Ranked list of enzme targets predicted to close the gap to the theoretical maximum rate of sucrose to starch conversion by > 50%. Ranked list of enzme targets (sucrolytic cleavage, glycolysis, or other pathways) to be taken forward in transgenic plants in EM3.1. Priority list of most effective combinations of transgenes from EM3.1, EM3.2, and EM3.3. | Oxford | Lee Sweetlove | Q2 2024 | Q2 2025 |  | Q2 2025 | Go/no-go: Can the model predict biochemical phenotypes of existing transgenic plants? Can the model deliver metabolic targets predicted to close the gap to the theoretical maximum rate of sucrose to starch conversion by > 50%?
3.4.3 | 0% | 0.7 | EM3.4: In silico analyses of sink metabolism-related transgenic lines being produced in the consortium | A ranked list of model-predicted gene combinations to inform stacking experiment prioritisation | Oxford | Lee Sweetlove |  | Q2 2028 |  | Q2 2028 | Go/no-go: Can the model rank engineering targets and provide a ranked list of target combinations?
TM1_Project management and central services
| PC | PS | TEAM OBJECTIVE | KEY RESULT (Metrics) | Assigned | Reporting Scientists | Start Date | Target Date | Dependencies (optional) | GoNoGo date | GoNoGo Metric
T1.1.1 | 40% | 0.7 | TM1.1: Assemble and deliver Quarterly Reports to Gates Ag One | Produce a report following the end of each quarter, two weeks ahead of each quarterly meeting summarising progress, challenges and next steps for each team objective. | FAU | Wolfgang Zierer/Uwe Sonnewald | Q2 2024 | Q2 2028 | - | Q2 2025 | Go/No-go: Are any improvements needed in the way reporting and communication is implemented within the project?
T1.1.2 | 40% | 0.7 | TM1.1: Quarterly Meetings with Gates Ag One | Attend a quarterly review meeting with the Gates Ag One team review the previous quarters report and providing a remediation plans as Go/no-go points are reached within the project. | FAU | Wolfgang Zierer/Uwe Sonnewald | Q2 2024 | Q2 2028 | -
T1.1.3 | 40% | 0.7 | TM1.1: Annual Reporting | Complete the Grant Investment Document to complement the quarterly reporting following each annual period in accordance with timings laid out in the grant agreement. | FAU | Wolfgang Zierer/Uwe Sonnewald | Q2 2024 | Q2 2028 | -
T1.1.4 | 40% | 0.7 | TM1.1: Financial Reporting | Complete financial reporting following each annual period in accordance with timings laid out in the grant agreement. | FAU | Wolfgang Zierer/Uwe Sonnewald | Q2 2024 | Q2 2028 | -
T1.1.5 | 40% | 0.7 | TM1.1: Annual Meeting | Conduct a whole project annual meeting each period. | FAU | Wolfgang Zierer/Uwe Sonnewald | Q2 2024 | Q2 2028 | -
T1.1.6 | 40% | 0.7 | TM1.1: Communications | Manage communcations in accordance with the grant agreement. | FAU | Wolfgang Zierer/Uwe Sonnewald | Q2 2024 | Q2 2028 | -
T1.1.7 | 40% | 0.7 | TM1.1: Intellectual Property management | Manage intellectual property disclosures in partnership with the Gates Ag One team in accordance with the grant agreement. | FAU | Wolfgang Zierer/Uwe Sonnewald | Q2 2024 | Q2 2028 | -
TM2_Cassava transformation
TM2.1_Routine transformation
| PC | PS | TEAM OBJECTIVE | KEY RESULT (Metrics) | Assigned | Reporting Scientists | Start Date | Target Date | Dependencies (optional) | GoNoGo date | GoNoGo Metric
T2.1.1 | 100% | 0.7 | TM2.1: Maintain successful delivery of transgenic lines in target cultivars. | Routine transformation of transformable cassava genotypes and maintainance of FEC and transformed lines. | ETH | Simon Bull | Q2 2024 | Q2 2025 | - | Q2 2025 | Go/No-go: Is the capacity and speed of transgenic production sufficient to meet the needs of the programme? Do we need to create or identify additional capacity to meet the timelines within the project?
T2.1.2 | 100% | 0.7 | TM2.1: Maintain successful delivery of transgenic lines in target cultivars. | Routine transformation of transformable cassava genotypes and maintainance of FEC and transformed lines. | ETH | Simon Bull | Q2 2025 | Q2 2026 | - | Q2 2026 | Go/No-go: Is the capacity and speed of transgenic production sufficient to meet the needs of the programme? Do we need to create or identify additional capacity to meet the timelines within the project?
T2.1.3 | 25% | 0.7 | TM2.1: Maintain successful delivery of transgenic lines in target cultivars. | Routine transformation of transformable cassava genotypes and maintainance of FEC and transformed lines. | ETH | Simon Bull | Q2 2026 | Q2 2027 | - | Q2 2027 | Go/No-go: Is the capacity and speed of transgenic production sufficient to meet the needs of the programme? Do we need to create or identify additional capacity to meet the timelines within the project?
T2.1.4 | 0% | 0.7 | TM2.1: Maintain successful delivery of transgenic lines in target cultivars. | Routine transformation of transformable cassava genotypes and maintainance of FEC and transformed lines. | ETH | Simon Bull | Q2 2027 | Q2 2028 | -
T2.1.4 | 0% | 0.7 | TM2.1: Maintain successful delivery of transgenic lines in target cultivars. | Routine transformation of transformable cassava genotypes and maintainance of FEC and transformed lines. | ETH | Simon Bull | Q2 2028 | Q2 2029 | -
TM2.2_Chemical and genetic boosters
| PC | PS | TEAM OBJECTIVE | KEY RESULT (Metrics) | Assigned |  | Start Date | Target Date | Dependencies (optional) | GoNoGo date | GoNoGo Metric
T2.2.1 | 45% | 0.7 | Utilize chemical boosters to enhance the regeneration efficiency of a SSA genotypes to facilitate a complete transformation cycle | Chemical boosters can be used to complete the transformation process of a previously untransformable SSA genotype (e.g. TMS91/02324, Baba70) | FAU | Christian Lamm | Q2 2025 | Q4 2027 |  | Q4 2027 | No-Go: Chemical boosters have no positive effect on the regeneration efficiency of SSA genotypes
T2.2.2 | 100% | 0.7 | Characterization of first TMS98/0505 transformations for general viability | Regnerate TMS98/0505 plantlets, test all plantlets for T-DNA integration, growth vitality, genomic stability, and CMD resistance | FAU | Christian Lamm | Q2 2025 | Q4 2025
T2.2.3 | 80% | 1 | Execute another round of TMS98/0505 (or similar SSA genotype) transformation and characterize the transgenic plant lines for general viability | Regnerate TMS98/0505 plantlets, test all plantlets for T-DNA integration, growth vitality, genomic stability, and CMD resistance | FAU | Christian Lamm | Q2 2025 | Q3 2026 |  | Q4 2026 | No-Go: Transformation of TMS98/0505 (or similar SSA genotype) does not produce viable (no obvious growth defects, no loss of CMD resistance) transgenic plants
T2.2.4 | 30% | 0.8 | Execute another round of TMS98/0505 (or similar SSA genotype) transformation and characterize the transgenic plant lines | Regnerate TMS98/0505 plantlets, test all plantlets for T-DNA integration, growth vitality, genomic stability, and CMD resistance | FAU | Christian Lamm | Q1 2026 | Q2 2027 | T2.2.3 Protocol is viable and Go/No-Go point can be met
T2.2.5 | 10% | 0.9 | Execute another round of TMS98/0505 (or similar SSA genotype) transformation and characterize the transgenic plant lines | Regnerate TMS98/0505 plantlets, test all plantlets for T-DNA integration, growth vitality, genomic stability, and CMD resistance | FAU | Christian Lamm | Q4 2026 | Q4 2027 | T2.2.3 Protocol is viable and Go/No-Go point can be met
T2.2.6 | 50% | 0.7 | Provide transgenic SSA cassava lines for confined field trials | Isolation of up to 30 plant lines with PCR valdiated T-DNA insertions and necessary multiplication to achieve required replicate numbers. | FAU | Christian Lamm | Q2 2025 | Q4 2027 | T2.2.3 Protocol is viable and Go/No-Go point can be met
TM2.3_Transformation of farmer-preferred genotypes
| PC | PS | TEAM OBJECTIVE | KEY RESULT (Metrics) | Assigned | Reporting Scientists | Start Date | Target Date | Dependencies (optional) | GoNoGo date | GoNoGo Metric
T2.3.1 | 60% | 0.3 | TM2.3: Further protocol optimization and first block of transformation attempts with farmer-preferred genotype(s) with CASS constructs including line selection and greenhouse testing. | Reach at least 10% transformation efficiency compared to the TMS60444 benchmark and obtained at least 10 plant lines for at least one CASS construct with full T-DNA integration and without negative side effects | NRCRI | Ihuoma Okwuonu | Q2 2024 | Q2 2025 |  | Q2 2025 | Go/No-Go 2.3.1: Can we demonstrate succesful transformation of at least one recalcitrant genotype at 10% transformation efficiency showing no major negative side effects including genome instatility or major growth defects?
T2.3.2 | 0% | 0.3 | TM2.3: Further protocol optimization and second block of transformation attempts of farmer-preferred genotype(s) with CASS constructs. Line selection and greenhouse testing. | Reach at least 20% transformation efficiency compared to the TMS60444 benchmark and obtained at least 20 plant lines per construct for at least two CASS constructs with full T-DNA integration and without negative side effects | NRCRI | Ihuoma Okwuonu | Q2 2025 | Q2 2026 |  | Q2 2026 | Go/No-go 2.3.2: Can we demonstrate succesful transformation of at least one recalcitrant genotype at 20% transformation efficiency showing no major negative side effects including genome instatility or major growth defects?
T2.3.3 | 0% | 0.3 | TM2.3: Further protocol optimization and third block of transformation attempts of farmer-preferred genotype(s) with CASS constructs. Line selection and greenhouse testing. | Reach at least 30% transformation efficiency compared to the TMS60444 benchmark and obtained at least 30 plant lines per construct for at least three CASS constructs with full T-DNA integration and without negative side effects | NRCRI | Ihuoma Okwuonu | Q3 2026 | Q3 2027 |  | Q3 2027 | Go/No-Go 2.3.3: Can we demonstrate succesful transformation of at least one recalcitrant genotype at 30% efficiency showing no major negative side effects including genome instatility or major growth defects?
T2.3.4 | 0% | 0.7 | TM2.3: Prepare CFT site and obtain permission to conduct confined field trial at NRCRI | Prepare CFT site and obtain permission to conduct confined field trial at NRCRI | NRCRI | Ihuoma Okwuonu | Q2 2025 | Q2 2026
T2.3.5 | 0% | 0.7 | TM2.3: Conduct confined field trial with CASS lines | Conduct growth performance tests with up to 30 cassava events, with 20 plantlets per event in triplicate within the confined field trial. Adhere to all NBMA regulations. | NRCRI | Ihuoma Okwuonu | Q2 2026 | Q2 2027
T2.3.6 | 0% | 0.7 | TM2.3: Prepare CFT site and obtain permission to conduct confined field trial at NRCRI | Prepare CFT site and renew permit to conduct confined field trial at NRCRI | NRCRI | Ihuoma Okwuonu | Q2 2026 | Q2 2027
T2.3.7 | 0% | 0.7 | TM2.3: Conduct another confined field trial with CASS lines | Conduct growth performance tests with up to 30 cassava events, with 20 plantlets per event in triplicate within the confined field trial. Adhere to all NBMA regulations. | NRCRI | Ihuoma Okwuonu | Q2 2027 | Q2 2028
Objective TM3_Expanding the cassava expression toolbox
TM3.1_Testing of already identified tissue-specific promoter candidates
| PC | PS | TEAM OBJECTIVE | KEY RESULT (Metrics) | Assigned | Reporting Scientists | Start Date | Target Date | Dependencies (optional) | GoNoGo date | GoNoGo Metric
3.1.1 | 100% | 0.7 | TM3.1: Cloning of 6 tissue-specific promoter candidates. Transformation of 6 tissue-specific promoter candidates. Greenhouse evaluation of 6 tissue-specific promoter candidates. | Isolation of up to 10 plant lines with GUS staining/GFP fluorescence to determine a consistent promoter activity pattern. | FAU | Wolfgang Zierer | Q2 2024 | Q4 2025
3.1.2 | 40% | 0.7 | TM3.1: Cloning of 5 additional tissue-specific promoter candidates. Transformation of 5 tissue-specific promoter candidates. Greenhouse evaluation of 5 tissue-specific promoter candidates. | Isolation of up to 10 plant lines with GUS staining/GFP fluorescence to determine a consistent promoter activity pattern. | FAU | Wolfgang Zierer | Q4 2025 | Q2 2027 |  | Q2 2026 | Go no-go: Is the success and speed of identifying tissue-specific promoters sufficient to meet the goals of the programme? Do we need to create or identify additional capacity to meet the timelines within the project?
3.1.3 | 0% | 0.7 | TM3.1: Cloning of 4 additional tissue-specific promoter candidates. Transformation of 4 tissue-specific promoter candidates. Greenhouse evaluation of 4 tissue-specific promoter candidates. | Isolation of up to 10 plant lines with GUS staining/GFP fluorescence to determine a consistent promoter activity pattern. | FAU | Wolfgang Zierer | Q2 2027 | Q4 2028
TM3.2_Identification of genes and promoter candidates involved in formation of xylem parenchyma
| PC | PS | TEAM OBJECTIVE | KEY RESULT (Metrics) | Assigned | Reporting Scientists | Start Date | Target Date | Dependencies (optional) | GoNoGo date | GoNoGo Metric
3.2.1 | 65% | 0.5 | TM3.2: Establishing cassava storage root protoplast isolation for three developmental stages | Obtaining 600-1200 cells/µl healthy protoplasts without sign of RNA degradation or cellular debris | HU | Ari Pekka Mähönen | Q2 2024 | Q4 2024
3.2.2 | 55% | 0.5 | TM3.2: Establishing cassava storage root nucleic sorting (only if M1 is not possible) | Obtaining isolated nuclei with high mRNA content and absence of cellular debris | HU | Ari Pekka Mähönen | Q4 2024 | Q2 2026 |  | Q2 2026 | Go no-go: Is the success and speed of identifying genes and promoter candidates involved in formation of xylem parenchyma sufficient to meet the goals of the programme? Do we need to create or identify additional capacity to meet the timelines within the project?
3.2.3 | 10% | 0.7 | TM3.2: Single cell transcriptome analysis. Bioinformatic data analysis. Single cell gene expression map in cassava storage root concluded. | Sequencing of approximately 15,000 good-quality cells or 10.000 good quality nuclei revealing single cell gene expression maps revealing the different gene expression profiles of the different storage root cell types in the different developmental stages | HU | Ari Pekka Mähönen | Q2 2025 | Q2 2026
Objective TM4_Cassava confined field testing
TM4.1_Pre-testing of transgenic lines outside Africa
| PC | PS | TEAM OBJECTIVE | KEY RESULT (Metrics) | Assigned | Reporting Scientists | Start Date | Target Date | Dependencies (optional) | GoNoGo date | GoNoGo Metric
T4.1.1 | 100% | 0.9 | TM4.1: Preparations for confined field-testing at NCHU season 2024. | Plant import permit, generated 5000-6000 in vitro plantlets, 5000-6000 in vitro plantlets arrive at NCHU with a transplanting survial rate ≥70%. At least 15 viable replications for field-testing available at planting time. Key nutrients (e.g. NPK) and key soil parameters (e.g. pH) analyzed and field maintains the soil quality of previous years. | NCHU/FAU/ External | Wilhelm Gruissem | - | -
T4.1.2 | 100% | 0.9 | TM4.1: Confined field-testing at NCHU season 2024. | Planted 400-600 stakes into another field, Planted 3000-4000 cassava plants. Growth updates via pictures every 2 month and UAV-RGB and LiCor data collected and provided to database and project partners. Agronomics performance data and molecular samples collected and provided to database and project partners. Intermediate harvest samples arrived at project partners. Agronomics performance data collected and provided to database and project partners and final harvest samples arrived at project partners. | NCHU/FZJ | Wilhelm Gruissem | - | Q4 2024
T4.1.3 | 100% | 0.9 | TM4.1: Preparations for confined field-testing at NCHU season 2025. | Plant import permit, generated 5000-6000 in vitro plantlets, 5000-6000 in vitro plantlets arrive at NCHU with a transplanting survial rate ≥70%. At least 15 viable replications for field-testing available at planting time. Key nutrients (e.g. NPK) and key soil parameters (e.g. pH) analyzed and field maintains the soil quality of previous years. | NCHU/FAU/ External | Wilhelm Gruissem | Q3 2024 | Q1 2025
T4.1.4 | 100% | 0.9 | TM4.1: Confined field-testing at NCHU season 2025. | Planted 400-600 stakes into another field, Planted 3000-4000 cassava plants. Growth updates via pictures every 2 month and UAV-RGB and LiCor data collected and provided to database and project partners. Agronomics performance data and molecular samples collected and provided to database and project partners. Intermediate harvest samples arrived at project partners. Agronomics performance data collected and provided to database and project partners and final harvest samples arrived at project partners. | NCHU/FZJ | Wilhelm Gruissem | Q2 2025 | Q2 2026 |  | Q2 2026 | Go/No-go: Is the capacity of field testing sufficient to meet the needs of the programme? Do we need to create or identify additional capacity to meet the timelines and goals within the project?
T4.1.5 | 100% | 0.9 | TM4.1: Preparations for confined field-testing at NCHU season 2026. | Plant import permit, generated 5000-6000 in vitro plantlets, 5000-6000 in vitro plantlets arrive at NCHU with a transplanting survial rate ≥70%. At least 15 viable replications for field-testing available at planting time. Key nutrients (e.g. NPK) and key soil parameters (e.g. pH) analyzed and field maintains the soil quality of previous years. | NCHU/FAU/ External | Wilhelm Gruissem | Q3 2025 | Q1 2026
T4.1.6 | 35% | 0.7 | TM4.1: Confined field-testing at NCHU season 2026. | Planted 400-600 stakes into another field, Planted 3000-4000 cassava plants. Growth updates via pictures every 2 month and UAV-RGB and LiCor data collected and provided to database and project partners. Agronomics performance data and molecular samples collected and provided to database and project partners. Intermediate harvest samples arrived at project partners. Agronomics performance data collected and provided to database and project partners and final harvest samples arrived at project partners. | NCHU/FZJ | Wilhelm Gruissem | Q2 2026 | Q2 2027 |  | Q2 2027 | Go/No-go: Is the capacity of field testing sufficient to meet the needs of the programme? Do we need to create or identify additional capacity to meet the timelines and goals within the project?
T4.1.7 | 0% | 0.7 | TM4.1: Preparations for confined field-testing at NCHU season 2027. | Plant import permit, generated 5000-6000 in vitro plantlets, 5000-6000 in vitro plantlets arrive at NCHU with a transplanting survial rate ≥70%. At least 15 viable replications for field-testing available at planting time. Key nutrients (e.g. NPK) and key soil parameters (e.g. pH) analyzed and field maintains the soil quality of previous years. | NCHU/FAU/ External | Wilhelm Gruissem | Q3 2026 | Q1 2027
T4.1.8 | 0% | 0.7 | TM4.1: Confined field-testing at NCHU season 2027. | Planted 400-600 stakes into another field, Planted 3000-4000 cassava plants. Growth updates via pictures every 2 month and UAV-RGB and LiCor data collected and provided to database and project partners. Agronomics performance data and molecular samples collected and provided to database and project partners. Intermediate harvest samples arrived at project partners. Agronomics performance data collected and provided to database and project partners and final harvest samples arrived at project partners. | NCHU/FZJ | Wilhelm Gruissem | Q2 2027 | Q2 2028 |  | Q2 2028 | Go/No-go: Is the capacity of field testing sufficient to meet the needs of the programme? Do we need to create or identify additional capacity to meet the timelines and goals within the project?
T4.1.9 | 0% | 0.7 | TM4.1: Preparations for confined field-testing at NCHU season 2028. | Plant import permit, generated 5000-6000 in vitro plantlets, 5000-6000 in vitro plantlets arrive at NCHU with a transplanting survial rate ≥70%. At least 15 viable replications for field-testing available at planting time. Key nutrients (e.g. NPK) and key soil parameters (e.g. pH) analyzed and field maintains the soil quality of previous years. | NCHU/FAU/ External | Wilhelm Gruissem | Q3 2027 | Q1 2028
T4.1.10 | 0% | 0.7 | TM4.1: Confined field-testing at NCHU season 2028. | Planted 400-600 stakes into another field, Planted 3000-4000 cassava plants. Growth updates via pictures every 2 month and UAV-RGB and LiCor data collected and provided to database and project partners. Agronomics performance data and molecular samples collected and provided to database and project partners. Intermediate harvest samples arrived at project partners. Agronomics performance data collected and provided to database and project partners and final harvest samples arrived at project partners. | NCHU/FZJ | Wilhelm Gruissem | Q2 2028 | Q2 2029
TM4.2_Testing of transgenic lines in Africa and transgenic crossing activities
| PC | PS | TEAM OBJECTIVE | KEY RESULT (Metrics) | Assigned | Reporting Scientists | Start Date | Target Date | Dependencies (optional) | GoNoGo date | GoNoGo Metric
T4.2.1 | 100% | 0.7 | TM4.2: Nominate best performing construct for a pilot crossing experiment. Apply for permission to conduct the transgenic crossing experiment at IITA. | Identify best performing lines and submit an NBMA application document. | IITA | Ismail Rabbi | - | - |  | Q3 2024 | Go/No-go: Has IITA received permission to conduct the confined field trial (crossing experiment) or is there a possibility to modify or appeal?
T4.2.2 | 100% | 0.5 | TM4.2: Obtain plant import permit. Transplant and pre-harden planting material. Conducting crossing experiment in screenhouses at IITA CFT site. | For each transgenic and WT genotype, we will plant at least 40 plants to achieve the planed ~100 seeds per crossing combination. Approximately 300 crosses will be carried out to achieve the the planed ~100 seeds per crossing combination. ≥100 seeds can be obtained for each crossing combination. | IITA | Ismail Rabbi | Q2 2024 | Q4 2024
T4.2.3 | 50% | 0.5 | TM4.2: F1 seedling nursery (multiplication of planting material) | Plant approx. 100 F1 seeds in small pots for determination of all parameters typically tracked in the IITA breeding program, with PCR on genomic DNA to determine the presence or absence of T-DNA and collect ≥5 stakes per F1 plant available for clonal evaluation. | IITA | Ismail Rabbi | Q1 2025 | Q3 2025
T4.2.4 | 0% | 0.5 | TM4.2: Clonal evaluation of F1 plants in small plots | Planting of 5 clones per F1 plant in small plots (1 x 5 meters) with 5 clones per F1 plant for determination of all parameters typically tracked in the IITA breeding program with PCR on genomic DNA to determine the presence or absence of T-DNA and total storage root yield (and other agronomic parameters) of clonally evaluated F1 plants. | IITA | Ismail Rabbi | Q4 2025 | Q2 2026 |  | Q2 2026 | Go/No-go: Is the capacity of field testing at IITA sufficient to meet the needs of the programme? Do we need to create or identify additional capacity to meet the timelines and goals within the project?
T4.2.5 | 0% | 0.7 | TM4.2: Nominate best performing construct for a second crossing experiment and apply for permission to conduct a second transgenic crossing experiment at IITA. | Identify best performing lines and submit an NBMA application document. | IITA | Ismail Rabbi | Q4 2025 | Q1 2026
T4.2.6 | 0% | 0.7 | TM4.2: Obtain plant import permit. Transplant and pre-harden planting material. Conducting crossing experiment in screenhouses at IITA CFT site. | For each transgenic and WT genotype, we will plant at least 40 plants to achieve the planed ~100 seeds per crossing combination. Approximately 300 crosses will be carried out to achieve the the planed ~100 seeds per crossing combination. ≥100 seeds can be obtained for each crossing combination. | IITA | Ismail Rabbi | Q2 2026 | Q1 2027
T4.2.7 | 0% | 0.7 | TM4.2: F1 seedling nursery (multiplication of planting material) | Plant approx. 100 F1 seeds in small pots for determination of all parameters typically tracked in the IITA breeding program, with PCR on genomic DNA to determine the presence or absence of T-DNA and collect ≥5 stakes per F1 plant available for clonal evaluation. | IITA | Ismail Rabbi | Q1 2027 | Q3 2027
T4.2.8 | 0% | 0.7 | TM4.2: Clonal evaluation of F1 plants in small plots | Planting of 5 clones per F1 plant in small plots (1 x 5 meters) with 5 clones per F1 plant for determination of all parameters typically tracked in the IITA breeding program with PCR on genomic DNA to determine the presence or absence of T-DNA and total storage root yield (and other agronomic parameters) of clonally evaluated F1 plants. | IITA | Ismail Rabbi | Q4 2027 | Q2 2028
T4.2.9 | 0% | 0.7 | TM4.2: Establish a confined field trial at IITA using transgenic virus-resistant cassava genotypes. This includes obtaining the field trial permit, import permit, plant transfer and pre-haredening, field-preparation steps and plant growth in the CFT site at IITA. Field phenotyping including all pre-harvest and agronomic data typically tracked in the IITA breeding program | Conduct a confined field trial in Nigeriausing transgenic virus-resistent cassava genotypes | IITA | Ismail Rabbi | Q4 2027 | Q2 2029 | Successful transformation of virus-resistant genotypes in any of the CASS transformation labs | Q2 2029
TM5_Cassava plant and field phenotyping
| PC | PS | TEAM OBJECTIVE | KEY RESULT (Metrics) | Assigned | Reporting Scientists | Start Date | Target Date | Dependencies (optional) | GoNoGo date | GoNoGo Metric
T5.1.1 | 100% | 0.9 | TM5.1: 11CO2-PET measurements for WT plants and transgenic cassava plants with alterations in transport | 11CO2-PET measurement laboratory is certified for transgenic plants. A first set of WT and transgenic cassava plants with alterations in assimilate transport is pre-grown in the greenhouse and transferred to FZJ. Assimilate allocation of a first set of WT and transgenic cassava plants with alterations in assimilate transport is analyzed. | FZJ | Rober Koller | - | Q3 2024 |  | Q3 2024 | Go/No-go: Can 11C-label distribution between tissues reliably be visualized and quantified?
T5.1.2 | 100% | 0.5 | TM5.1: Comparative 11CO2-PET measurements between controls and transgenic cassava plants with alterations in transport | A second set of WT and transgenic cassava plants with alterations in assimilate transport is pre-grown in the greenhouse and transferred to FZJ. Assimilate allocation of a first set of WT and transgenic cassava plants with alterations in assimilate transport is analyzed. Qualitative and quantitative 11C-label distribution data for different plant tissues (esp. stem and roots) | FZJ | Rober Koller | Q3 2024 | Q4 2024 |  | Q1 2025 | Go/No-go: Are 11CO2-PET measurements able to reveal differences in assimilate allocation between different genotypes?
T5.1.3 | 50% | 0.7 | TM5.1: 11CO2-PETmeasurements can be accessed annualy with a subset of plant lines | Routine application of 11CO2-PET to characterize a selection of transgenic cassava plants. | FZJ | Rober Koller | Q2 2024 | Q1 2029
T5.1.4 | 50% | 0.7 | TM5.1: Plant level photosynthesis measurements and UAV data collection and evaluation is performed annually | Routine mapping of the field with UAV-RGB camera. Extraction of structural canopy parameters from UAV-RGB data (height, volume, growth rates) and timely delivery to project partners. Routine measurements of leaf photosynthesis with LiCor instrument. | FZJ | Uwe Rascher | Q2 2024 | Q1 2029 |  | Q2 2026 | Go/No-go: Is the current routine field phenotyping sufficient to meet the needs of the program or are improvements necessary?
TM6_Research data management
| PC | PS | TEAM OBJECTIVE | KEY RESULT (Metrics) | Assigned | Reporting Scientists | Start Date | Target Date | Dependencies (optional) | GoNoGo date | GoNoGo Metric
T6.1.1 | 100% | 0.7 | TM6.1: Period 1 data captured and workshop on system usage conducted. Improve the implementation of features related to lab results. Improve the visibility and accessibility of OMICS datasets for users. | Data implemented in database and users trained. Features implemented in database. | BTI | Lukas Mueller | Q2 2024 | Q3 2025
T6.1.2 | 75% | 0.7 | TM6.1: Period 2 data captured and workshop on system usage conducted. Improve the implementation of features related to lab results. Improve the visibility and accessibility of OMICS datasets for users. | Data implemented in database and users trained. Features implemented in database. | BTI | Lukas Mueller | Q2 2025 | Q3 2026 |  | Q2 2026 | Go/No-go: Is user engagment with CASSbase and the functionality of data management tools sufficent to meet the needs of the programme? Do we need to create or identify additional capacity to meet the timelines and goals within the project?
T6.1.3 | 15% | 0.7 | TM6.1: Period 3 data captured and workshop on system usage conducted. Release improved expression atlas tools that include processing of expression data online and additional analysis tools, such as better calling of over and under expressed genes. | Data implemented in database and users trained. Improved expression atlas launched. | BTI | Lukas Mueller | Q2 2026 | Q3 2027
T6.1.4 | 0% | 0.7 | TM6.1: Period 4 data captured. Release of improved query tools for all integrated data in the database. | Data implemented in database. Improved query tools launched. | BTI | Lukas Mueller | Q2 2027 | Q2 2028